## Sheet1
TSPi Time Recording Log – Form LOGT
Name |  |  | SMART PACKING LOT SYSTEM |  |  |  |  | Date |  | 2016-10-01
Team |  |  | Team CMU TPM3 Plus |  |  |  |  | Instructor |  | Van Luong Vo
Part/Level |  |  | Calc/Module |  |  |  |  | Cycle |  | 1
Date |  | Start | Stop | Interruption | Delta | Phase/ | Comp-onent |  | Comments
|  |  |  | Time | Time | Task
Week 1 |  |  |  |  | 8:00
day 1 | 2016-10-01 | 8:00 | 16:00 |  | 8:00 | Requirement,Scope (Complete Automation And Interation
Week 2 |  |  |  |  | 40:00
day 1 | 2016-10-03 | 8:00 | 16:00 |  | 8:00 | Scope (Complete Automation And Interation,Web Layout Design,Database Structuring Of Element Search, Global Search & Other Search Integrasion, source codes
day 2 | 2016-10-04 | 8:00 | 16:00 |  | 8:00 | Web Layout Design,Database Structuring Of Element Search, Global Search & Other Search Integrasion,Design Finalation & Additional Information Pages ,source codes
day 3 | 2016-10-05 | 8:00 | 16:00 |  | 8:00 | Web Layout Design,Database Structuring Of Element Search, Global Search & Other Search Integrasion,Design Finalation & Additional Information Pages , source codes, Programming documents
day 4 | 2016-10-06 | 8:00 | 16:00 |  | 8:00 | Web Layout Design,Database Structuring Of Element Search, Design Finalation & Additional Information Pages , source codes, Programming documents | Calc |  | Implement
day 5 | 2016-10-07 | 8:00 | 16:00 |  | 8:00 | Web Layout Design,Database Structuring Of Element Search, Design Finalation & Additional Information Pages, source codes, Programming documents
Week 3 |  |  |  |  | 40:00
day 1 | 2016-10-10 | 8:00 | 16:00 |  | 8:00 | Layout design, Detail admin database table and schema, source codes, Programming documents
day 2 | 2016-10-11 | 8:00 | 16:00 |  | 8:00 | Layout design, Admin Field & Reporting System, Design Finalation & Additional help pages, Backup & achieve management, source codes, Programming documents
day 3 | 2016-10-12 | 8:00 | 16:00 |  | 8:00 | Layout design, source codes, functional modules, Programming documents
day 4 | 2016-10-13 | 8:00 | 16:00 |  | 8:00 | Layout design, source codes, functional modules, Programming documents | Calc |  | Implement
day 5 | 2016-10-14 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules, Programming documents
Week 4 |  |  |  |  | 40:00
day 1 | 2016-10-17 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules, Programming documents
day 2 | 2016-10-18 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules, Programming documents
day 3 | 2016-10-19 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules, Programming documents
day 4 | 2016-10-20 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules | Calc |  | Implement
day 5 | 2016-10-21 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules
Week 5
day 1 | 2016-10-24 | 8:00 | 16:00 |  | 8:00 | circulation, serials management, Standards Integration, source codes, functional modules, Programming documents
day 2 | 2016-10-25 | 8:00 | 16:00 |  | 8:00 | Unit testing
day 3 | 2016-10-26 | 8:00 | 16:00 |  | 8:00 | Unit testing
day 4 | 2016-10-27 | 8:00 | 16:00 |  | 8:00 | Unit testing | Calc |  | Implement
day 5 | 2016-10-28 | 8:00 | 16:00 |  | 8:00 | Unit testing,Integration testing
Week 6 |  |  |  |  | 120:00
day 1 | 2016-10-31 | 8:00 | 16:00 |  | 8:00 | Unit testing, Integration testing | Calc |  | Implement
day 2 | 2016-11-01 | 8:00 | 16:00 |  | 8:00 | Unit testing, Integration testing | “ |  | “
day 3 | 2016-11-02 | 8:00 | 16:00 |  | 8:00 | Unit testing, Integration testing | “ |  | “
day 4 | 2016-11-03 | 8:00 | 16:00 |  | 8:00 | Unit testing, Integration testing
day 5 | 2016-11-04 | 8:00 | 16:00 |  | 8:00 | Integration testing
Week 7 |  |  |  |  | 40:00
day 1 | 2016-11-07 | 8:00 | 16:00 |  | 8:00 | Integration testing | Calc |  | Implement
day 2 | 2016-11-08 | 8:00 | 16:00 |  | 8:00 | Integration testing | “ |  | “
day 3 | 2016-11-09 | 8:00 | 16:00 |  | 8:00 | Integration testing | “ |  | “
day 4 | 2016-11-10 | 8:00 | 16:00 |  | 8:00 | Unit testing
day 5 | 2016-11-11 | 8:00 | 16:00 |  | 8:00 | Unit testing, System testing
Week 8 |  |  |  |  | 40:00
day 1 | 2016-11-14 | 8:00 | 16:00 |  | 8:00 | System testing | Calc |  | Implement
day 2 | 2016-11-15 | 8:00 | 16:00 |  | 8:00 | System testing | “ |  | “
day 3 | 2016-11-16 | 8:00 | 16:00 |  | 8:00 | System testing | “ |  | “
day 4 | 2016-11-17 | 8:00 | 16:00 |  | 8:00 | System testing
day 5 | 2016-11-18 | 8:00 | 16:00 |  | 8:00 | System testing
Week 9 |  |  |  |  | 40:00
day 1 | 2016-11-21 | 8:00 | 16:00 |  | 8:00 | System testing | Calc |  | Implement
day 2 | 2016-11-22 | 8:00 | 16:00 |  | 8:00 | System testing | “ |  | “
day 3 | 2016-11-23 | 8:00 | 16:00 |  | 8:00 | Installation | “ |  | “
day 4 | 2016-11-24 | 8:00 | 16:00 |  | 8:00 | Installation, Training & Tutorial
day 5 | 2016-11-25 | 8:00 | 16:00 |  | 8:00 | Training & Tutorial,
Week 10 |  |  |  |  | 2:00
day 1 | 2016-11-28 | 8:00 | 10:00 |  | 2:00 | Implementation | Calc |  | Implement